## Hardware
1. Estimated TASK
EVT Phase |  |  | Full feature development phase according to product requirements. Purpose: Bring up all product features and performance
I would like to estimate the list of tasks in the project that I mentioned below
| Stt | TASK | Description | Hour
HW Design | 1 | Learn and plan project design, Complete on Schematic for the project | Specification, comparison with similar project, finding reference design | 3
| 2 |  | Working on schematic | 8
| 3 |  | Updating ports and nets | 5
| 4 |  | Schematic preliminary checking | 3
| 5 |  | Updating and creating components | 3
| 6 |  | Fixing compiled errors and warning | 3
| 7 |  | Schematic checking | 3
| 8 |  | Updating schematic after preliminary checking | 7
| 9 | Create PCB for project and arrange component Demo for circuit. | Footprint checking | 4
| 10 |  | Component placement | 6
| 11 |  | Preliminary layout | 6
| 15 | Wiring demo of the processor (SD CARD + Ethernet +...) | Processor signal fanout – processor | 7
| 16 | Wiring demo of the EMMC | Processor signal eMMC | 4
|  | Wiring demo of MCU | Processor signal LVDS convert HDMI for Screen | 4
| 17 | Wiring demo of MCU | Processor signal MCU and Module Audio | 3
| 18 | Wiring demo of peripheral | Processor signal other (QSPI, UART, JTAG, SPI, I2C, PWM, USB, GPIO) | 3
| 19 | Finishing preliminary layout | Finishing preliminary layout | 3
| 26 | Check for complete PCB | Memory layout checking | 3
| 27 |  | Optimizing layout – top & bottom | 3
| 28 |  | Manufacturing optimizing | 3
| 29 | Simulation | Simulation PI(Hyperlynx) | 3
| 30 | Export files for production | Releasing Board | 3
|  |  | TOTAL | 90
Wage Estimate (EVT Phase)
Note |  |  | Recommend: Stack up PCB 4-6 layers